## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
China Viola | Team lead | v.china@alustudent.com
Memory Chungulo | Team member | m.chungulo@alustudent.com
Yves Isite | Team member | y.isite@alustudent.com
Esther Konde | Team member | e.konde@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Backend data pipeline, team participation sheet | China Viola | 10/13/26 | Completed | Yes | She completed her tasks in time and ensured everyone is dong their roles.
| Frontedn dashboard, PDF Dcumentation. | Memory Chungulo | 10/13/26 | Completed | Yes | She very supportive and always ensured we got our tasks done.
| Custom algorithm and backend setup, Database design and configuration. | Yves Isite | 10/13/26 | Completed | Yes | He was very supportive helping the team understand the concepts and work guide as well.
| API routes implementation, PDF documentation. | Esther Konde | 10/13/26 | Completed | Yes | She completed her tasks on time, and did her best to ensure every API route was seamlessly implemented and perfectly documented.
|  | [Name] | [Date]
|  | [Name] | [Date]
|  | [Name] | [Date]
|  | [Name] | [Date]
|  | [Name] | [Date]
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-05-10 | Understanding the assignment and splitting tasks | Yves Isite | All group members showed up | Went through the NYC Taxi brief and rubric together. Agreed on the four parts: data cleaning, database schema, backend API, frontend dashboard. Assigned an owner to each and confirmed everyone installs CodeVibe before coding. | Each member sets up VS Code, Git, and CodeVibe. Yves creates the shared repo and adds everyone as collaborators.
2026-10-10 | Reviewing what each one has done so far and rendering support | China Viola | All group members showed up | Checked progress on each part. Reviewed the repo structure and the cleaning and schema drafts. Discussed how the backend and frontend connect, and agreed each person writes their own section by hand rather than sharing code directly. | Members continue their assigned sections. Resolve environment setup issues raised during the meeting. Align on the database choice before loading data.
2026-12-10 | Reviewing what each one has done so far and rendering support | Memory Chungulo | All group members showed up | Reviewed updated work from each member. Looked at outstanding items on cleaning and the API endpoints. Flagged what still needs finishing before testing begins. | Finish remaining endpoints and dashboard filters. Prepare for a full test run of the system on 10/13.
10/13/26 | Testing and making final conclusions | Yves Isite | All group members showed up | Testing | To finalize and submit
10/14/26 | Making final changes and submitting in | Esther Konde | All group members showed up | Submission | [Follow-up Actions]